## Sheet2 (hidden)
File Status | Fily Type | Category | Owner of the action
Completed | Final | Database | Mario
Archived | Legacy | Data cleansing | Rober
Work in progress | Other | Data Exploration & Analysis | Dani
|  | Data Visualisation | Andres
|  | Submission | ALL
|  | Project Planning | Mario/Rober
Mario/Dani
Mario/Andres
Rober/Dani
Rober/Andres
Dani/Andres

## Tracker
Name | Category | Description | File Type | File Status | Action | Owner of the Action
| Project Planning |  |  | Completed | Create account on GitHub | ALL
| Project Planning |  |  | Completed | Create project team on GitHub | Mario
| Project Planning |  |  | Completed | Create Excel Tracker | Andres
| Project Planning |  |  | Completed | Create Project Plan Draft | Dani/Andres
| Project Planning |  |  | Work in progress | Get familiar with the challenge | ALL
| Project Planning |  |  | Completed | Decide analysis and tools | ALL
| Data cleansing |  |  | Work in progress | Create list of questions from database/challenge | ALL
| Data cleansing |  |  | Work in progress | Data Exploration Pre-cleaning | ALL
| Data cleansing |  |  | Work in progress | Split file into train and test files | ALL
| Data cleansing |  |  | Work in progress | Start data cleansing | ALL
| Project Planning |  |  | Completed | Structure of files and drive (GitHub)
Data Exploration R Markdown | Data Exploration & Analysis |  |  | Work in progress | Start data exploration | ALL
| Data Visualisation |  |  | Work in progress | Data Exploration (Dashboard) | ALL
if (!require(package)) install.packages("package") library(package)
Crear variable
Rename Sales
Note on F17: Autor: will install package if it doesn't exist, and then load it

## List of questions
Question | Analysis
What factors influence on turnover? | Logistic regression coefficients
What variables can be controlled by the company, which can't? What should the company focus on to manage turnover? | After doing the logistic regression, and getting a coefficient for each variable that significantly impacts on turnover, determine which of those can be controlled by the company
What is the turnover rate? | Turnover formula
Where are the hotspots of turnover? | Descriptive statistics for turnover
Who is leaving? Are we keeping or letting our high-performers go? | Visualise leavers by performance
Are there any differences of turnover by area (department)? | ANOVA
What is the cost of turnover? | Assign $ to salary levels, and calculate estimate of cost of turnover (maybe a what if scenario modelling in power BI/tableau/qlik)?
Do all the analysis we did for turnover…but for satisfaction level! | This time multiple regression
Predict turnover | Log Regression, Decision Tree, Random Forest
How can employees be segmented? | Cluster analysis
Create variable projects/time_spend_company | Check relationship with average monthly hours
Average monthly hours and accidents? Hours/average projects?
Is turnover higher during first year of time_spend_company?
Predict work accident
Predict promotions

## Wish List
Wish | Requester
Cross-validation | Mario/Rober
Bigger database - 10k-200k | Andres
Focus on logistic regression | Mario/Andres
Power BI que compare performance de diferentes modelos | Mario
Visually improve our Markdowns (perhaps by adding a dashboard or using shiny?) | Andres
ANOVA's (no tenemos codigo de ese analisis) | Andres
Power BI - use the highlight and bookmarking features | Andres
Publish final documents | Dani
Biplot logistico | Dani/Mario
Github | Mario
Analysis |  | Mario | Rober | Dani | Andres
Logistic Regression | DONE | X | X
Decision Tree | DONE
Random Forest | DONE
Biplot |  |  | X | X
Discriminant Analysis |  |  | X
Correspondence Analysis |  |  |  | X
Cluster Analysis | IN PROGRESS |  |  | X | X
Tools
R
R Markdown
Tableau
Power BI
Qlik
Ggplot 2
SPSS
Note on B25: Autor: For next projects: Shiny

## Data Science Process
what we know… |  |  |  |  | what we want to predict…
COMBI
| train_cleaned |  |  |  | test_cleaned
train
+
+
test
Dataset |  | Description
COMBI |  | - The result of merging the original training and testing datasets - After having cleaned the combined data, the data is split again into the 'train_cleaned' and 'test_cleaned' datasets - Manipulated and used when we want to modify/use variables in both, the 'train_cleaned' and 'test_cleaned' datasets at the same time
train_cleaned |  | - This dataset is used to create our models - This dataset can be split into the 'train' and 'test' datasets if we want to assess the performance of our models
test_cleaned |  | - This dataset is used to apply our model to a dataset "unseen" by the model and submit our model's predictions to kaggle
train |  | - The result of splitting the 'train_cleaned' dataset into a train and test datasets - Used to generate the model for the first time
test |  | - The result of splitting the 'train_cleaned' dataset into a train and test datasets - Used to assess the performance of the model
Steps |  | Data Science Process |  |  |  | Logistic Regression | Decision Tree | Random Forest | Discriminant Analysis
1 |  | Combine original training and testing datasets into a COMBI dataset |  |  |  | No | No | No | No
2 |  | Clean the COMBI database |  |  |  | No | No | No | No
3 |  | Split the COMBI database into the train_cleaned and test_cleaned datasets |  |  |  | No | No | No | No
4 |  | Split the train_cleaned dataset into the train and test datasets |  |  |  | No | No | No | No
5 |  | Use the train dataset to create the models |  |  |  | No | No | No | No
6 |  | Predict values in the test dataset using the model created in the train dataset |  |  |  | No | No | No | No
7 |  | Assess performance of the models in the test dataset |  |  |  | No | No | No | No
8 |  | Compare prediction accuracy in the test dataset vs prediction accuracy for the train dataset to avoid overfitting |  |  |  | No | No | No | No
9 |  | Apply final model to train_cleaned (please note that previously had only been done using the train dataset, which is a subset of the train_cleaned dataset) |  |  |  | No | No | No | No
10 |  | Make predictions on the test_cleaned dataset by using the final model which was generated using the train_cleaned dataset |  |  |  | No | No | No | No
11 |  | Submit the predictions of your final model on the test_cleaned dataset to Kaggle |  |  |  | No | No | No | No

## Main Info
https://github.com/warbelt/Human_Resources_Analytics-Kaggle_DS